## Tracker
Validation Report - Kestrel and Co. Website - Phase 1 - Staging
Solution ID | Requirement | Status | Findings by cycle | Exception agreed | Action on | ETA | Sign-off
KES-S001 | Every page load on the website | Passed | 22 May: Page name arrives on the home page and the listing pages but is empty on every product page. The object is set by a later script. 29 May: Product pages now populate. Login status still Anonymous for a signed in customer on the account pages. 04 Jun: All eleven global objects present on all page types. |  |  | Signed
KES-S002 | Every virtual page load in the cart and checkout | Partly passed | 22 May: The direct call fires on the first load as well as on each step change, so the checkout counts one page view too many. 29 May: Fixed on delivery and payment. Still double counting on the first cart view. 04 Jun: Cart view fixed. Named Day delivery view has no virtual page load at all, and that view was not in the walkthrough. | Named Day view deferred to the Phase 1 patch release, agreed 04 Jun. | Kestrel web dev | 2026-06-12
KES-S003 | A product is clicked on a listing page | Passed | 22 May: Direct call fires twice on every click, so product clicks are exactly double. 29 May: Fires once. Listing type is Category Listing on the search results page. 04 Jun: Correct on all four listing types. |  |  | Signed
KES-S004 | A product detail page is viewed | Passed | 22 May: Page load rule fires before the product objects exist, so every product view is empty. Changed to a direct call, see TSD change log 2. 29 May: Populates correctly. 04 Jun: Confirmed on twelve products across three categories. |  |  | Signed
KES-S005 | A product is added to the cart from the product page | Passed | 22 May: Quantity is the cart total rather than the quantity being added, so a second add of the same product sends 2. 29 May: Correct. 04 Jun: Confirmed including quantity above one. |  |  | Signed
KES-S006 | A product is added to the cart from the quick view overlay | Passed | 22 May: Cart source is Product Page rather than Quick View, so the two cannot be told apart. 29 May: Correct. 04 Jun: Confirmed. |  |  | Signed
KES-S007 | A product is removed from the cart | Passed | 22 May: The whole cart is sent on a removal, so removing one product reports all of them removed. 29 May: Correct. 04 Jun: Confirmed. |  |  | Signed
KES-S008 | The cart page is viewed | Passed | 22 May: Product string holds one entry with three IDs joined by commas inside it. 29 May: Rebuilt as an array, see TSD change log 3. Correct. 04 Jun: Confirmed with one, three and eleven products. |  |  | Signed
KES-S009 | The checkout is started | Passed | 22 May: Fires again every time the customer goes back a step, inflating checkouts. 29 May: Fires once. 04 Jun: Confirmed. |  |  | Signed
KES-S010 | The delivery step is completed | Passed | 22 May: Delivery charge is missing when the charge is zero, because the site treats zero as nothing to send. 29 May: Zero now sent as zero. 04 Jun: Confirmed on all four options including showroom collection. |  |  | Signed
KES-S011 | The payment step is completed | Passed | 22 May: Payment method arrives as the gateway code rather than the name. 29 May: Names correct for card and PayPal, still a code for Klarna. 04 Jun: All five correct. |  |  | Signed
KES-S012 | An order is completed | Passed | 22 May: Refreshing the confirmation page sends a second purchase, so revenue on the test account was double. 29 May: Guard added, see TSD change log 4. No duplicate across twenty refreshes. 04 Jun: Confirmed. Revenue matches the order system on all fourteen test orders. |  |  | Signed
KES-S013 | A payment fails | Partly passed | 22 May: No call at all. The failure view is served by the gateway and the site never regains control. 29 May: The gateway now returns to a site page and the call fires. Failure reason is a numeric code. 04 Jun: Card Declined and Cancelled by Customer map correctly. The three gateway timeout codes still arrive as numbers. | Numeric timeout codes accepted for launch and classified in reporting instead, agreed 04 Jun. | Kestrel web dev | 2026-06-26 | Signed
KES-S014 | A discount code is applied | Passed | 22 May: Fires on a rejected code as well as an accepted one. 29 May: Fires only on accepted. 04 Jun: Confirmed on three codes. |  |  | Signed
KES-S015 | A search is run on the site | Passed | 22 May: Result count arrives as a string, so no null search was ever recorded. 29 May: Rewritten, see TSD change log 5. Null searches now recorded. 04 Jun: Confirmed. Bucket processing rule correct. |  |  | Signed
KES-S016 | A search result is clicked | Passed | 22 May: Position counts from zero. 29 May: Counts from one. 04 Jun: Confirmed including promoted results. |  |  | Signed
KES-S017 | A customer signs in | Passed | 22 May: Customer ID is the raw email address. Stopped testing and raised immediately. 29 May: Hashed on the server. Raw address no longer present anywhere in the data layer. 04 Jun: Confirmed on all four sign in methods. |  |  | Signed
KES-S018 | A new customer registers | Passed | 22 May: No call. 29 May: Fires, but also on a failed registration. 04 Jun: Fires only on a created account. |  |  | Signed
KES-S019 | A customer signs out | Failed | 22 May: No call. 29 May: No call. 04 Jun: Still no call. The session is cleared and the page reloads before the tag manager can see anything. |  | Kestrel web dev | 2026-06-19
KES-S020 | A home page banner is clicked | Passed | 22 May: Banner position is the campaign slot from the content system rather than the position on the page, so the same banner reports the same position everywhere. 29 May: Correct. 04 Jun: Confirmed. |  |  | Signed
KES-S021 | A navigation link is clicked | Passed | 22 May: Footer links do not fire. Header and main menu correct. 29 May: All three fire. Navigation level is Main Menu for footer links. 04 Jun: Correct. |  |  | Signed
KES-S022 | A showroom is looked up | Passed | 22 May: Showroom city is the showroom location rather than the city searched for. 29 May: Correct. 04 Jun: Confirmed on eight searches. |  |  | Signed
KES-S023 | A form is started and a form is submitted | Ignored | 22 May: Direct call identifiers are formStart and formComplete rather than form_start and form_submit. Data element names also differ. 29 May: No change. 04 Jun: No change. The form component is owned by a third party and the change is not in their release window. | Dropped from Phase 1 entirely. The trade account form is the only form in scope and it will be covered in the Phase 1 patch release. Agreed 04 Jun. | Kestrel web dev | Phase 1 patch
KES-S024 | An error is shown to the customer | Passed | 22 May: Page not found fires but carries no URL, so the report says only that something was missing. 29 May: URL present. 04 Jun: Gateway and form validation errors also confirmed. |  |  | Signed
KES-S031 | Marketing channel processing rules | Passed | 29 May: Paid search traffic is landing in Natural Search because the paid rule sits below the natural one. 04 Jun: Order corrected. All nine channels resolve. |  |  | Signed
KES-S032 | Campaign code classifications | Passed | 04 Jun: Uploaded and applied. Twelve campaign codes classified, four with no name yet. |  | Kestrel marketing | pre launch | Signed
KES-S033 | Search results bucket processing rule | Passed | 04 Jun: Applied. Buckets correct at zero, three, eleven and forty results. |  |  | Signed
KES-S038 | Consent gate on every rule | Passed | 29 May: Two rules fire before consent is answered. 04 Jun: All rules gated. No hit before an answer. |  |  | Signed
Template from amitdusane.com ¦ Amit G Dusane
Note on A3: The solution ID from the SDR. Not a new number. This is what makes the whole chain checkable.
Note on B3: Copied from the SDR so the row can be read without opening another document.
Note on C3: Passed, Failed, Partly passed or Ignored, as at the latest cycle.
Note on D3: Every cycle, dated, newest at the bottom. Never overwrite the previous finding. The history is what shows whether a fix worked or moved the problem.
Note on E3: Something agreed as acceptable rather than fixed. An exception is a decision and it needs to be written down.
Note on F3: Who has to act next. Blank means nobody, which means it is done.
Note on G3: When the fix is expected.
Note on H3: Filled in by the Kestrel business team, not by the analytics team.

## Summary
Summary - Phase 1 as at 04 June 2026
Status | Count | What it means here
Passed | 24 | Behaves as the SDR says, across three cycles, with evidence captured.
Partly passed | 2 | Works for the main case. A named part does not, and the part is written down with an owner and a date.
Failed | 1 | Does not work. KES-S019 sign out. Still open with Kestrel and Co.
Ignored | 1 | Dropped from this phase by agreement, with a reason and a date. KES-S023 form tracking.
Total solutions tested | 28 | Twenty four rules and four configuration items.
Cycles run | 3 | 22 May, 29 May, 04 June. All on staging.
Faults found in cycle 1 | 26 | Of twenty eight solutions tested, two were correct first time.
Faults still open | 4 | Two exceptions accepted, one failure, one solution dropped.
Go live recommendation | Proceed | Twenty six of twenty eight solutions are usable. The two that are not are written down, owned and dated, so nobody discovers them in a report in August and calls the whole implementation unreliable.
Template from amitdusane.com ¦ Amit G Dusane